## Feedback Assessment
Item # | Role/Section | Screen/Tab | Change Requested | Details | Status in Latest Build | Gap Analysis | Effort to Fix
0 | Trader | New Deal > Transaction Type dropdown | Revise dropdown options to: 1) Buy, 2) Sell. Remove Tomorrow, Spot, Today. | The Tomorrow, Spot, Today options are already reflected on the deal date and Value date fields, so they should be removed from this dropdown. | NOT IMPLEMENTED | Current build still has Today/Tomorrow/Spot as transaction types. Need to: (1) Change transaction_type values to 'Buy' and 'Sell', (2) Update seed data, (3) Update all frontend references and report filters. | Medium
1 | Admin | Reference Data tab | Add a new field called 'Counterparty' | Pertains to which PJL Group company will be transacting the deal (CLSC/PJ/Verite etc.) Should appear as a new tab alongside Companies, Banks, Transaction Types, Transfer Types, Currencies. | NOT IMPLEMENTED | No 'Counterparty' reference data entity exists. Need to: (1) Create counterparties collection in DB + Couchbase scope mapping, (2) CRUD API endpoints, (3) Admin UI tab in Reference Data page, (4) Seed initial counterparty values. | Medium
2 | Trader | New Deal > Source (From) - FX Local | Remove 'Company' field, replace with 'Counterparty' dropdown | The Source (From) 'Company' dropdown becomes 'Counterparty'. | NOT IMPLEMENTED | Current build shows 'Company' in Source (From). Need to: (1) Conditionally show 'Counterparty' dropdown (from new counterparties ref data) instead of 'Company' when transfer_type is FX Local. (2) Store counterparty_id on the deal. | Medium
3 | Trader | New Deal > Ours (Receiving Account) - FX Local | Add auto-populated Counterparty display field | Example: 'Counterparty: Cebuana Lhuillier Services Corp' - a fixed, uneditable field reflecting the chosen counterparty. | NOT IMPLEMENTED | Current Ours section has no counterparty display. Need to: (1) Add a read-only field showing the selected counterparty name in the Ours section when transfer_type is FX Local. | Easy
4 | Trader | New Deal > FX Inter-Company transfer type | Replace 'Company' with 'Counterparty' in both Source (From) and Destination (To) | A new Transfer Type 'FX-Intercompany' was created via admin access. Both Source and Destination should show Counterparty instead of Company. | PARTIALLY IMPLEMENTED | FX Bank Deal transfer type exists but FX-Intercompany does not. Need to: (1) Seed 'FX-Intercompany' transfer type, (2) When this type is selected, replace Company with Counterparty in both Source and Destination sections. | Medium
5 | Trader | New Deal > FX Inter-Company > Ours | Rename existing Ours box to 'Selling Counterparty Ours (Receiving Account)' | The existing Ours box gets renamed based on transfer type. | NOT IMPLEMENTED | Current label is always 'Ours (Receiving Account)'. Need to: (1) Dynamically change the Ours card title based on transfer_type. When FX-Intercompany: 'Selling Counterparty Ours (Receiving Account)'. | Easy
6 | Trader | New Deal > FX Inter-Company | Add entirely new box: 'Buying Counterparty Ours (Receiving Account)' | A second Ours section is needed for the buying counterparty in FX Inter-Company deals. | NOT IMPLEMENTED | No second Ours section exists. Need to: (1) Add a new card 'Buying Counterparty Ours (Receiving Account)' with Bank/Account fields, (2) Store these fields on the deal (e.g., buying_ours_bank, buying_ours_account_num), (3) Backend model update. | High
7 | Reports | Settlement Report | FX Inter-company entry shows two line entries | One SALE line and one BUY line with the same reference number (suffixed .1 and .2). The only change between lines is the transaction_type column. | NOT IMPLEMENTED | Settlement report currently shows one row per deal. Need to: (1) Detect FX-Intercompany deals, (2) Duplicate the row with .1 and .2 reference suffixes, (3) Set transaction_type to 'Sell' for .1 and 'Buy' for .2. | Medium
8 | Reports | Settlement Report | Add TMS-patterned Report for SAP mass upload | A TMS-tailored report capturing only the fields required for SAP mass upload. Similar to Settlement Report but with specific column filtering. | NOT IMPLEMENTED | No TMS report exists. Need to: (1) Define the exact TMS/SAP required columns (need user input), (2) Create new report endpoint, (3) Add to reports page. Requires clarification on exact TMS column mapping. | Medium
9 | Trader | New Deal > Amounts & Currency box | Simplify currency section: (1) Single currency dropdown (Buy/Sell label based on Txn Type), (2) Remove second currency selector, (3) Remove currency codes from amount labels, (4) Formula = Currency Amount x Rate only (remove divide logic) | The simplified layout shows: single currency dropdown, Currency Amount, Exchange Rate, and Converted Amount (no currency codes in labels). The previously requested divide function should be removed. | CONFLICTS WITH PRIOR IMPLEMENTATION | Current build has: dual currency selectors (Buy + Sell), auto-divide when Buy=PHP, currency codes in labels. This item REVERSES several prior implementations (Items 3, 4 from previous assessment). Need to: (1) Replace dual currency with single dropdown labeled 'Buy Currency' or 'Sell Currency' based on transaction type, (2) Remove divide logic, (3) Remove currency code labels from amount fields. IMPORTANT: Confirm with user before removing previously requested features. | Medium
SUMMARY
Total Items: | 10
Not Implemented: | 8
Partially Implemented: | 1
Conflicts with Prior: | 1
KEY DEPENDENCIES & NOTES
1. Items 1-6 are interconnected: Counterparty entity must be created first (Item 1), then Items 2-6 depend on it.
2. Item 0 (Transaction Type change) affects the entire deal model — Buy/Sell replaces Today/Tomorrow/Spot.
3. Item 9 REVERSES previous assessment Items 3 & 4 (divide formula, dual currency). Confirm before implementing.
4. Item 8 (TMS Report) requires clarification on exact SAP column mapping from the user.
5. Items 4-7 introduce FX-Intercompany as a complex transfer type with dual Ours sections and split settlement lines.